## AML上线步骤
AML上线
任务标识 | 任务状态 | 实际完成时间 | 任务名称 | 开始时间 | 完成时间 | 前置任务 | 执行人 | 复核人 | 备注
1 | 未完成 |  | 申请主机服务（EAST、EASTRRB）与备机密码 | 2020-04-24 19:00 | 2020-04-24 19:05 |  | 罗启斌 | SylviaZ | 主机 133.11.131.34
2 | 未完成 |  | 申请EAST数据库密码 | 2020-04-24 19:00 | 2020-04-24 19:05 |  | 罗启斌 | SylviaZ | 主机 133.11.148.94 cn000zhj1320 EAST生产
3 |  |  | 停止主机服务
3.1 | 未完成 |  | EAST、EASTRRB | 2020-04-24 19:05 | 2020-04-24 19:10 |  | 罗启斌 | SylviaZ | CN000ZHJ1323 133.11.131.34 EAST生产 su wasadm /opt/IBM/wlp/bin/server stop
4 |  |  | 数据库部分 |  |  | 1
4.1 | 未完成 |  | 跑数据库脚本 | 2020-04-24 19:10 | 2020-04-24 19:15 |  | 罗启斌 | SylviaZ | 脚本.sql
5 |  |  | 数据迁移准备 |  |  | 2
5.1 | 已完成 |  | 无
6 |  |  | 后台追批量 |  |  | 3
6.1 | 已完成 |  | 无
7 |  |  | 配置文件
7.1 | 已完成 |  | 无
8 |  |  | 前端应用服务启动 |  |  | 4,5
8.1 | 未完成 |  | 备份EAST（133.11.131.34）war包 备份EASTRRB（133.11.131.33）war包 | 2020-04-24 19:15 | 2020-04-24 19:25 |  | 罗启斌 | SylviaZ
8.2 | 未完成 |  | 上传war包到EAST（133.11.131.34） 上传war包EASTRRB（133.11.131.33） | 2020-04-24 19:25 | 2020-04-24 19:35 |  | 罗启斌 | SylviaZ
8.3 | 未完成 |  | 部署EAST（133.11.131.34） 部署EASTRRB（133.11.131.33） | 2020-04-24 19:35 | 2020-04-24 19:45 |  | 罗启斌 | SylviaZ
8.4 | 未完成 |  | 服务启动 | 2020-04-24 19:50 | 2020-04-24 20:00 |  |  |  | /opt/IBM/wlp/bin/server start
9 |  |  | 检查 |  |  | 6
9.1 | 未完成 |  | 数据库数据检查 | 2020-04-24 20:00 | 2020-04-24 20:05 |  | 罗启斌 | SylviaZ
9.2 | 未完成 |  | 前端应用检查 | 2020-04-24 20:05 | 2020-04-24 20:10 |  | 罗启斌 | SylviaZ
9.3 | 未完成 |  | 业务人员检查 | 2020-04-24 20:10 | 2020-04-24 20:15
10 | 未完成 |  | 备机部署 上传war包到EAST（133.10.217.1） 上传war包EASTRRB（133.10.217.2） | 2020-04-24 20:15 | 2020-04-24 20:20 | 7 | 罗启斌 | SylviaZ

## 回滚步骤
反洗钱发布失败回滚
任务标识 | 任务状态 | 实际完成时间 | 任务名称 | 开始时间 | 完成时间 | 前置任务 | 执行人 | 复核人 | 备注
1 |  |  | 数据部分
| 已完成 |  | 无 | 2020-04-24 19:50 | 2020-04-24 20:00
2 |  |  | 前端应用服务启动 |  |  | 1
2.1 | 未完成 |  | 还原EAST（133.11.131.34）上一个版本的war包 还原EASTRRB（133.11.131.33）上一个版本的war包 | 2020-04-24 20:05 | 2020-04-24 20:10 |  | 罗启斌 | SylviaZ
2.2 | 未完成 |  | 服务启动 | 2020-04-24 20:10 | 2020-04-24 20:20 |  | 罗启斌 | SylviaZ | /opt/IBM/wlp/bin/server start
3 |  |  | 检查 |  |  | 2
3.1 | 未完成 |  | 数据库数据检查 | 2020-04-24 20:20 | 2020-04-24 20:25 |  | 罗启斌 | SylviaZ
3.2 | 未完成 |  | 前端应用检查 | 2020-04-24 20:25 | 2020-04-24 20:30 |  | 技术 | 技术
3.3 | 未完成 |  | 业务人员检查 | 2020-04-24 20:30 | 2020-04-24 20:40 |  | 业务 | 业务

## 验证步骤
验证
任务标识 | 任务状态 | 实际完成时间 | 任务名称 | 开始时间 | 完成时间 | 前置任务 | 执行人 | 复核人 | 备注
1 | 未完成 |  | 导入EXCEL/文本文件 | 2020-04-24 20:00 | 2020-04-24 20:05 |  | 罗启斌 | SylviaZ
1.1 | 未完成 |  | 登入EAST系统上传EXCEL文本文件，验证上传数据格式 | 2020-04-24 20:05 | 2020-04-24 20:30 |  | 罗启斌 | SylviaZ | 1.PROJECT_LOAN_SHH_YYYYMMDD(项目贷款模板)。删除TOT_INV_AMT_LCY、CAP_AMT_LCY、PROJ_LOAN_AMT_LCY、COMP_TOT_INV_AMT_LCY、COMP_CAP_AMT_LCY字段。 2.SYN_SHH_YYYYMM(银团贷款模板)。删除SQDKZE。

## 脚本清单
| 改动内容 | 备注
需要添加的表结构
添加配置数据 | delete tb_tableinfo t where t.file_name like '%PROJECT_LOAN_SHH%';
delete tb_tableinfo t where t.file_name like '%SYN_SHH%';
insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'COUN_CODE', null, null, null, null, 1, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'GROU_MEME', null, null, null, null, 2, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'BRAN_CODE', null, null, null, null, 3, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'CUST_SERI', null, null, null, null, 4, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'LIMI_GROUP', null, null, null, null, 5, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'LIMI_TYPE', null, null, null, null, 6, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'LIMI_LINE', null, null, null, null, 7, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'PROJ_NAME', null, null, null, null, 8, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'PROJ_TYPE', null, null, null, null, 9, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'SYN_LOAN', null, null, null, null, 10, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'TOTA_INVE_CCY', null, null, null, null, 11, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'TOTA_INVE_AMT', null, null, null, null, 12, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'CAP_CCY', null, null, null, null, 13, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'CAP_CCY_AMT', null, null, null, null, 14, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'PROJ_LOAN_CCY', null, null, null, null, 15, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'PROJ_LOAN_AMT', null, null, null, null, 16, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'PROJ_LOAN_B_DATE', null, null, null, null, 17, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'PROJ_LOAN_E_DATE', null, null, null, null, 18, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'APPR_NO', null, null, null, null, 19, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'PROJ_APPR', null, null, null, null, 20, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'PLAN_LICEN_NO', null, null, null, null, 21, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'CON_LAND_LICEN_NO', null, null, null, null, 22, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'EIA_LICEN_NO', null, null, null, null, 23, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'CON_PER_NO', null, null, null, null, 24, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'OTH_PER_LAND', null, null, null, null, 25, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'OTH_PER_NO', null, null, null, null, 26, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'START_DATE', null, null, null, null, 27, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'COMP_TOTA_INVE_CCY', null, null, null, null, 28, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'COMP_TOTA_INVE_AMT', null, null, null, null, 29, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'COMP_CAP_CCY', null, null, null, null, 30, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('PROJECT_LOAN_SHH', 'E_PROJECT_LOAN', 'COMP_CAP_CCY_AMT', null, null, null, null, 31, null, null, null, null);
insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('SYN_SHH', 'E_SYNDICATED_LOAN', 'XDHTH1', null, null, null, null, 1, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('SYN_SHH', 'E_SYNDICATED_LOAN', 'XDHTH2', null, null, null, null, 2, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('SYN_SHH', 'E_SYNDICATED_LOAN', 'XYQSRQ', null, null, null, null, 3, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('SYN_SHH', 'E_SYNDICATED_LOAN', 'XYZZRQ', null, null, null, null, 4, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('SYN_SHH', 'E_SYNDICATED_LOAN', 'SQDKZE1', null, null, null, null, 5, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('SYN_SHH', 'E_SYNDICATED_LOAN', 'SQDKZE2', null, null, null, null, 6, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('SYN_SHH', 'E_SYNDICATED_LOAN', 'ZBXXM', null, null, null, null, 7, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('SYN_SHH', 'E_SYNDICATED_LOAN', 'DLXXM', null, null, null, null, 8, null, null, null, null); insert into TB_TABLEINFO (FILE_NAME, TABLE_NAME, COLUMN_NAME, DATA_TYPE, DATA_LENGTH, COMMENTS, DATA_DIC, ORDNUM, TWO_SEVEN, IS_NOT_NULL, IS_NOT_PK, IS_ONLY) values ('SYN_SHH', 'E_SYNDICATED_LOAN', 'CDXXM', null, null, null, null, 9, null, null, null, null); commit;

## 系统环境说明
WAS环境信息
Hostname | IP Address | 说明
CN000IFC1232 | 133.10.217.1 | HBCNAML备份
CN000IFC1233 | 133.10.217.2 | RRBAML备份
CN000ZHJ1322 | 133.11.131.33 | HBCNAML生产
CN000ZHJ1323 | 133.11.131.34 | RRBAML生产
数据库环境信息
用户 | 密码 | 地址
eastrrb | oracle | cnrac59-scan.gss5.hk.hsbc:2001/pcnhbcn.cn.hsbc
easthbcn | oracle | cnrac59-scan.gss5.hk.hsbc:2001/pcnrrba1.cn.hsbc